## Invoice
To, |  | BILL No. |  | : GJ/2025-26/63
AQUATECH SYSTEMS (ASIA) PVT. LTD. |  | BILL DATE |  | : 28.12.2025
Altimus, 601-602, 6th Floor, Besides |  | Work Order No. |  | : E-10055 - 300003430
Embassy Market |  | Work Order Date |  | : 22 July , 2025
Shreyas Colony, Navrangpura |  | GSTN NO. |  | : 24AAQCS3102E1ZP
GSTIN NO : 24AABCA1850C2ZE |  | SAC NO. |  | : 995442
|  | PAN NO. |  | : AAQCS3102E
|  | RA |  | :06
SR.NO | DESCRIPTION | UOM | QTY | RATE | AMOUNT
1 | Installation Cost | PU | 1 |  | 5988092.8
SITE-E-10055-Adani Water Ltd.(62MLD)
HSN/SAC:
PR/ITEM: / 00000
|  | TOTAL AMOUNT |  |  | 5988092.8
|  | CGST 9% |  |  | 538928.352
|  | SGST 9% |  |  | 538928.352
|  | TOTAL RECEIVABLE |  |  | 7065949.504
Rs.In Words | Seventy-Lakh Sixty Five Thousnd Nine Hundred Forty Nine Rupees And Fifty Paise Only.
For SANTHOSH FABRICATORS PVT. LTD.
Authorised Signatory

## Abs
SANTHOSH FABRICATORS PVT. LTD.
CLIENT: | Aquatech System (Asia) Pvt. Ltd. |  | PO.NO.: E-10055 - 300003430 |  |  | P.O DATE: 22 July, 2025 |  |  | BILL NO: | :GJ/2025-26/63
Project : | E-10055-Adani Water Ltd. |  | 62MLD |  |  | R.A. Bill No.: 06 |  |  | BILL DATE | : 25.11.25
SL.NO. | DESCRIPTION | UOM | PO /QTY | RATE | AMOUNT | QUANTITY |  |  | AMOUNT
[6 empty] | UPTO PREV | IN THIS BILL | UPTO DATE | UPTO PREV | THIS BILL | UPTO DATE
A | E-10055-DW-MD-AE-002P1-P sheet 5 of 65
1 | Lamella clarifier | Nos | 4320 | 140 | 604800 | 0 | 0 | 0 | 0 | 0 | 0
2 | Agiatator for Flash mixer basin-Motor will be loose supply | Nos | 5 | 14960 | 74800 | 0 | 0 | 0 | 0 | 0 | 0
3 | Agiatator for Flocculator basin basin-Motor will be loose supply | Nos | 5 | 36960 | 184800 | 0 | 0 | 0 | 0 | 0 | 0
B | E-10055-DW-AE-002P1-P sheet 6 of 65 | [5 empty] | 0
4 | Media filter feed pumps | Nos | 5 | 155936 | 779680 | 3.5 | 0 | 3.5 | 545776 | 0 | 545776
C | E-10055-DW-AE-002P1-P sheet 7 to 09 of 65
5 | Dual Media Filter ( Installation and Alignment) | Nos | 18 | 418000 | 7524000 | 18 | 0 | 18 | 7524000 | 0 | 7524000
6 | ANTHRACITE | Nos | 18 | 59840 | 1077120 | 18 | 0 | 18 | 1077120 | 0 | 1077120
7 | QUARTZ SAND | Nos | 18 | 119816 | 2156688 | 18 | 0 | 18 | 2156688 | 0 | 2156688
8 | GARNET SAND | Nos | 18 | 70798 | 1274364 | 18 | 0 | 18 | 1274364 | 0 | 1274364
9 | GRAVEL | Nos | 18 | 20439 | 367902 | 18 | 0 | 18 | 367902 | 0 | 367902
10 | GRAVEL | Nos | 18 | 18571 | 334278 | 18 | 0 | 18 | 334278 | 0 | 334278
D | E-10055-DW-AE-002P1-P sheet 10 to 12 of 65
11 | Pressure Sand Filter ( Installation and Alignment) | Nos | 18 | 418000 | 7524000 | 18 | 0 | 18 | 7524000 | 0 | 7524000
12 | QUARTZ SAND | Nos | 18 | 269938 | 4858884 | 18 | 0 | 18 | 4858884 | 0 | 4858884
13 | GRAVEL | Nos | 18 | 20439 | 367902 | 18 | 0 | 18 | 367902 | 0 | 367902
14 | GRAVEL | Nos | 18 | 70798 | 1274364 | 18 | 0 | 18 | 1274364 | 0 | 1274364
E | E-10055-DW-AE-002P1-P sheet 17 of 65 | [5 empty] | 0
14 | DMF Backwash pump | Nos | 3 | 41784 | 125352 | 0 | 0 | 0 | 0 | 0 | 0
15 | PSF Backwash pump | Nos | 3 | 41784 | 125352 | 0 | 0 | 0 | 0 | 0 | 0
F | E-10055-DW-AE-002P1-P sheet 18 of 65
16 | DMF Backwash Airblower | Nos | 3 | 26976 | 80928 | 2.5 | 0 | 2.5 | 67440 | 0 | 67440
17 | PSF Backwash Airblower | Nos | 3 | 26976 | 80928 | 2.5 | 0 | 2.5 | 67440 | 0 | 67440
G | E-10055-DW-AE-002P1-P sheet 19 of 65
18 | SWRO Micron Cartridge filters | Nos | 8 | 62400 | 499200 | 8 | 0 | 8 | 499200 | 0 | 499200
H | E-10055-DW-AE-002P1-P sheet 20 of 65
19 | SWRO-Pressure Tube with victaulic coupling, saddle , strap etc. | Nos | 896 | 4656 | 4171776 | 128 | 256 | 384 | 595968 | 1191936 | 1787904
20 | SWRO-Membranes | Nos | 7672 | 725 | 5562200 | 0 | 0 | 0 | 0 | 0 | 0
I | E-10055-DW-AE-002P1-P sheet 21 of 65
21 | SWRO High pressure Pump with motor | Nos | 7 | 178128 | 1246896 | 2.25 | 3.2 | 5.45 | 400788 | 570009.6 | 970797.6
22 | RO-ERD Booster Pump with motor | Nos | 7 | 81936 | 573552 | 2.25 | 3.2 | 5.45 | 184356 | 262195.2 | 446551.2
23 | ERD (Energy Recovery Unit) | Nos | 77 | 5000 | 385000 | 0 | 0 | 0 | 0 | 0 | 0
24 | Suck Bank tank | Nos | 21 | 42000 | 882000 | 3 | 6 | 9 | 126000 | 252000 | 378000
J | E-10055-DW-AE-002P1-P sheet 24 of 65
25 | BWRO Feed pump with motor | Nos | 6 | 40800 | 244800 | 0 | 0 | 0 | 0 | 0 | 0
K | E-10055-DW-AE-002P1-P sheet 25 of 65 | [5 empty] | 0
26 | SWRO Permeate water Transfer pump with motor | Nos | 3 | 34200 | 102600 | 0 | 0 | 0 | 0 | 0 | 0
L | AE-10055-DW-AE-002P1-P sheet 26 of 65 | [5 empty] | 0
27 | BWRO Micron Cartridge filters | Nos | 6 | 31200 | 187200 | 0 | 0 | 0 | 0 | 0 | 0
M | AE-10055-DW-AE-002P1-P sheet 27 of 65 | [5 empty] | 0
28 | Hydrophore | Nos | 1 | 9500 | 9500 | 0 | 0 | 0 | 0 | 0 | 0
N | AE-1087-DW-AE-002P1-P sheet 29 of 65 | [5 empty] | 0
29 | BWRO HP-Pump with motor | Nos | 5 | 73944 | 369720 | 0 | 0 | 0 | 0 | 0 | 0
30 | BWRO-Pressure Tube with victaulic coupling, saddle , strap etc. | Nos | 245 | 4850 | 1188250 | 0 | 0 | 0 | 0 | 0 | 0
31 | BWRO-Membranes | Nos | 1715 | 725 | 1243375 | 0 | 0 | 0 | 0 | 0 | 0
O | AE-1087-DW-AE-002P1-P sheet 30 of 65 | [5 empty] | 0
32 | Lime stone filter Feed pumps | Nos | 4 | 55608 | 222432 | 0 | 0 | 0 | 0 | 0 | 0
P | AE-1087-DW-AE-002P1-P sheet 31 to 33 of 65 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Lime Stone filter | Nos | 12 | 175008 | 2100096 | 12 | 0 | 12 | 2100096 | 0 | 2100096
34 | Lime stone media | Kg | 432597.36 | 4 | 1730389.44 | 200000 | 124448 | 324448 | 800000 | 497792 | 1297792
Q | AE-1087-DW-AE-002P1-P sheet 36 of 65 | [5 empty] | 0
36 | Final Product water transfer pump with motor | Nos | 3 | 140832 | 422496 | 0 | 0 | 0 | 0 | 0 | 0
R | AE-1087-DW-AE-002P1-P sheet 37 of 65 | [5 empty] | 0
37 | Lime stone Back wash Air blowers | Nos | 2 | 20256 | 40512 | 0 | 0 | 0 | 0 | 0 | 0
38 | RO-CIP Preparation Tank | Nos | 1 | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0
39 | Agiatator for RO-CIP Preparation Tank | Nos | 1 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0
40 | RO-CIP Chemical Transfer pump | Nos | 1 | 7920 | 7920 | 0 | 0 | 0 | 0 | 0 | 0
S | AE-1087-DW-AE-002P1-P sheet 38 of 65 | [5 empty] | 0
41 | RO CIP Tank | Nos | 1 | 12000 | 12000 | 0.75 | 0 | 0.75 | 9000 | 0 | 9000
42 | RO CIP PUMP | Nos | 2 | 53208 | 106416 | 0 | 0 | 0 | 0 | 0 | 0
43 | RO -CIP Cartridge Filter | Nos | 1 | 58800 | 58800 | 0 | 0 | 0 | 0 | 0 | 0
T | AE-1087-DW-AE-002P1-P sheet 39 of 65 | [5 empty] | 0
44 | Sludge Collection Transfer Pump | Nos | 2 | 84984 | 169968 | 0 | 0 | 0 | 0 | 0 | 0
U | AE-1087-DW-AE-002P1-P sheet 40 of 65 | [5 empty] | 0
45 | N-PIT Transfer pump | Nos | 2 | 17217.6 | 34453.56 | 0 | 0 | 0 | 0 | 0 | 0
V | AE-1087-DW-AE-002P1-P sheet 41 of 65 | [5 empty] | 0
46 | Reject Disposal pumps | Nos | 4 | 157704 | 630816 | 2.8 | 0 | 2.8 | 441571.2 | 0 | 441571.2
W | AE-1087-DW-AE-002P1-P sheet 42 of 65 | [5 empty] | 0
47 | CO2 Storage tank with internal piping | Nos | 2 | 192000 | 384000 | 0 | 0 | 0 | 0 | 0 | 0
48 | Vaporised skid with piping | Nos | 1 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0
49 | CISX skid with piping and instrumenet | Nos | 1 | 42500 | 42500 | 0 | 0 | 0 | 0 | 0 | 0
50 | Regrigeneration unit | Nos | 2 | 9360 | 18720 | 0 | 0 | 0 | 0 | 0 | 0
51 | Internal I/C piping-SS piping with Insulation | Lot | 1 | 115000 | 115000 | 0 | 0 | 0 | 0 | 0 | 0
X | AE-1087-DW-AE-002P1-P sheet 43 of 65 | [5 empty] | 0
53 | Carrier water Transfer pump | Nos | 2 | 12888 | 25776 | 0 | 0 | 0 | 0 | 0 | 0
Y | AE-1087-DW-AE-002P1-P sheet 44 of 65 | [5 empty] | 0
54 | Self cleaning filter | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
55 | Chorination booster pump | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
56 | Electrolyzer | Nos | 2 | 47760 | 95520 | 0 | 0 | 0 | 0 | 0 | 0
Z | AE-1087-DW-AE-002P1-P sheet 45A of 65 | [5 empty] | 0
57 | Hypo Tank | Nos | 2 | 7200 | 14400 | 0 | 0 | 0 | 0 | 0 | 0
58 | Continuous /shock Dosing pump | Nos | 3 | 5448 | 16344 | 0 | 0 | 0 | 0 | 0 | 0
59 | Air blowers | Nos | 4 | 3120 | 12480 | 0 | 0 | 0 | 0 | 0 | 0
A1 | AE-1087-DW-AE-002P1-P sheet 45B of 65 | [5 empty] | 0
60 | Acid Dosing Tank- 2 m3 | Nos | 2 | 7200 | 14400 | 0 | 0 | 0 | 0 | 0 | 0
61 | Acid Wash Pump | Nos | 2 | 5448 | 10896 | 0 | 0 | 0 | 0 | 0 | 0
62 | Fume Absorber | Nos | 1 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0
B2 | AE-1087-DW-AE-002P1-P sheet 47 of 65 | [5 empty] | 0
63 | Air Compressor | Nos | 2 | 22944 | 45888 | 0 | 0 | 0 | 0 | 0 | 0
64 | Air Dryer | Nos | 2 | 6888 | 13776 | 0 | 0 | 0 | 0 | 0 | 0
65 | Prefilter, Post Filter, ACF | Nos | 3 | 13500 | 40500 | 0 | 0 | 0 | 0 | 0 | 0
66 | Wet Air Receiver 1M3 | Nos | 2 | 7680 | 15360 | 0 | 0 | 0 | 0 | 0 | 0
67 | Air Receiver Tank 10 m3 | Nos | 1 | 70800 | 70800 | 0 | 0 | 0 | 0 | 0 | 0
C3 | AE-1087-DW-AE-002P1-P sheet 48 of 65 | [5 empty] | 0
68 | The pneumatic Lime conveying system consists of below mentioned major structure, equipment, and associated piping, valve etc. | [5 empty] | 0
69 | Diverter valve assembly- 80NB ( Valve With Piping) | Set | 11 | 1500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0
70 | Big Bag Handling structure with bag filter-1 | Set | 1 | 9840 | 9840 | 0 | 0 | 0 | 0 | 0 | 0
71 | Big Bag Handling structure with bag filter- 2 | Set | 1 | 11520 | 11520 | 0 | 0 | 0 | 0 | 0 | 0
72 | Big Bag Handling structure with bag filter- 3 | Set | 1 | 11520 | 11520 | 0 | 0 | 0 | 0 | 0 | 0
73 | Bag Filter-1- C-fan | Set | 1 | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | 0
74 | Bag Filter-2- C-fan | Set | 1 | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | 0
75 | Bag Filter-3- C-fan | Set | 1 | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | 0
76 | Rotary feeder below Bag Filter | Set | 3 | 1680 | 5040 | 0 | 0 | 0 | 0 | 0 | 0
77 | Main storage Hopper/ silo with structural assembly | Set | 1 | 48000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0
78 | Batch / Surge Hopper | Nos | 1 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0
79 | Rotary feeder below Storage Silo | Set | 1 | 2880 | 2880 | 0 | 0 | 0 | 0 | 0 | 0
80 | Vent Filter Blower- | Nos | 1 | 4800 | 4800 | 0 | 0 | 0 | 0 | 0 | 0
81 | Air Receiver Tank 1 m3 | Nos | 1 | 24480 | 24480 | 0 | 0 | 0 | 0 | 0 | 0
82 | Air Dryer | Nos | 1 | 9600 | 9600 | 0 | 0 | 0 | 0 | 0 | 0
83 | Dense Phase Tranporter | Nos | 1 | 9840 | 9840 | 0 | 0 | 0 | 0 | 0 | 0
84 | Structural platform | Ton | 2 | 75000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0
85 | CS pipin Pre fabricated | Lot | 1 | 145000 | 145000 | 0 | 0 | 0 | 0 | 0 | 0
D4 | AE-1087-DW-AE-002P1-P sheet 50 of 65 | [5 empty] | 0
86 | FeCl3 Bulk Storage Tank with ladder & handrail | Nos | 2 | 93600 | 187200 | 2 | 0 | 2 | 187200 | 0 | 187200
87 | FeCl3 Unloading CUM Transfer pump | Nos | 6 | 5500 | 33000 | 0 | 0 | 1.5 | 0 | 0 | 8250
E5 | AE-1087-DW-AE-002P1-P sheet 51 of 65 | [5 empty] | 0
88 | Fecl3 Dosing tank | Nos | 2 | 7200 | 14400 | 1 | 0 | 1 | 7200 | 0 | 7200
89 | Fecl3 doing pump | Nos | 3 | 7500 | 22500 | 0 | 0 | 0 | 0 | 0 | 0
F6 | AE-1087-DW-AE-002P1-P sheet 52 of 65 | [5 empty] | 0
90 | Polymer Dosing Sysytem With Tank, Agitataor & Screw Feder | Nos | 3 | 12960 | 38880 | 3 | 0 | 3 | 38880 | 0 | 38880
G7 | AE-1087-DW-AE-002P1-P sheet 53 of 65 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | Polymer Dosing pump for Flocculator | NOS | 6 | 7200 | 43200 | 0 | 0 | 0 | 0 | 0 | 0
H8 | AE-1087-DW-AE-002P1-P sheet 54 of 65 | [5 empty] | 0
92 | Antiscalant Transfer pump | NOS | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0
93 | Antiscalant dosing tank | NOS | 2 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
94 | Antiscalant dosing pump-SWRO | Nos | 3 | 5000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0
95 | Antiscalant dosing pump-BWRO | Nos | 2 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
I9 | AE-1087-DW-AE-002P1-P sheet 55 of 65 | [5 empty] | 0
96 | SBS Dosing tank | Nos | 2 | 10200 | 20400 | 2 | 0 | 2 | 20400 | 0 | 20400
97 | SBS Dosing pump-SWRO | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
98 | Agitataor for SBS Dosing pump | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
99 | EYE Wash and Safety shower | Nos | 1 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0
J10 | AE-1087-DW-AE-002P1-P sheet 56 of 65 | [5 empty] | 0
100 | HCL Bluk storage tank with ladder & Handrail | Nos | 2 | 81600 | 163200 | 2 | 0 | 2 | 163200 | 0 | 163200
101 | HCL Unloading cum transfer pump | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
101 | EYE Wash and Safety shower | Nos | 1 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0
102 | Flume Absorber | Nos | 1 | 1250 | 1250 | 0 | 0 | 0 | 0 | 0 | 0
K11 | AE-1087-DW-AE-002P1-P sheet 57 of 65 | [5 empty] | 0
103 | HCL Dosing tank | Nos | 2 | 8400 | 16800 | 0 | 0 | 0 | 0 | 0 | 0
104 | HCL Dosing pump for Clarifier | Nos | 3 | 5500 | 16500 | 0 | 0 | 0 | 0 | 0 | 0
105 | HCL Dosing pump for N-PIT | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
L12 | AE-1087-DW-AE-002P1-P sheet 58 of 65 | [5 empty] | 0
106 | NAOH Bulk storage tank with ladder & Handrail | Nos | 2 | 54000 | 108000 | 2 | 0 | 2 | 108000 | 0 | 108000
107 | NaOH Unloading cum transfer pump | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
108 | EYE Wash and Safety shower | Nos | 1 | 5500 | 5500 | 0 | 0 | 0 | 0 | 0 | 0
M13 | AE-1087-DW-AE-002P1-P sheet 59 of 65 | [5 empty] | 0
109 | NAOH Dosing tank | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
110 | NAOH Dosing pump-BWRO | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
111 | NAOH-Dosing pump for Final product water | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
N14 | AE-1087-DW-AE-002P1-P sheet 60 of 65 | [5 empty] | 0
112 | NAOH Dosing pump for SWRO Product water | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
113 | NAOH Dosing pump for -N-PIT | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
O15 | AE-1087-DW-AE-002P1-P sheet 61 of 65 | [5 empty] | 0
114 | Biocide dosing tank | Nos | 2 | 5500 | 11000 | 2 | 0 | 2 | 11000 | 0 | 11000
115 | Biocide dosing pump | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
P16 | AE-1087-DW-AE-002P1-P sheet 62 of 65 | [5 empty] | 0
116 | NaOCl Bulk storage tank with ladder & Handrail | Nos | 2 | 42000 | 84000 | 2 | 0 | 2 | 84000 | 0 | 84000
117 | NaOCl Unloading cum transfer pump | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
Q17 | AE-1087-DW-AE-002P1-P sheet 63 of 65 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | NAOCL Dosing tank | Nos | 2 | 5500 | 11000 | 2 | 0 | 2 | 11000 | 0 | 11000
119 | NAOCL Dosing pump-SWRO | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
120 | NAOCL Dosing pump for Final product water | Nos | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0
R18 | PIPING |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Piping fabrication, Installation, and alignment with Stud, Nut, Hex. bolt, Washer, Gasket, U bolt, PP spacer, RO, Mixing quill, etc., including hydrotest for site fabricated piping and leak test for prefabricated piping. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | CPVC Piping- Including Hydrotest | Inch-dia | 54840 | 170 | 9322800 | 0 | 0 | 0 | 0 | 0 | 0
122 |  | Inch mtr | 11316 | 180 | 2036880 | 0 | 0 | 0 | 0 | 0 | 0
123 | GI Piping-Including Pneumatic test | Inch-dia | 2050 | 325 | 666250 | 0 | 0 | 0 | 0 | 0 | 0
124 |  | Inch Mtr | 6060 | 200 | 1212000 | 0 | 1320.8 | 1320.8 | 0 | 264160 | 264160
125 | SS-316L Piping-Inclusding Hydrotest | Inch-dia | 300 | 625 | 187500 | 0 | 0 | 0 | 0 | 0 | 0
126 |  | Inch-mtr | 5500 | 200 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0
127 | Duplex & Super Duplex Piping -Including Hydrotest | Inch-dia | 500 | 850 | 425000 | 0 | 0 | 0 | 0 | 0 | 0
128 |  | Inch mtr | 6500 | 200 | 1300000 | 500 | 0 | 500 | 100000 | 0 | 100000
129 | Valves,Calibration column,Pulsation dampner-5000 Qty | Inch-dia | 10000 | 260 | 2600000 | 0 | 0 | 0 | 0 | 0 | 0
130 | Online Flow transmeter-100 Qty | Inch dia | 1000 | 254 | 254000 | 0 | 0 | 0 | 0 | 0 | 0
S19 | MONORAIL / EOT CRANE | [5 empty] | 0
131 | MONORAIL / EOT CRANE | [5 empty] | 0
132 | EOT Crane 3 Ton (Single Girder Crane for DMF Pump House) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
133 | Monorail beam with electrical hoist 1 Ton including cable trolly (Sludge tarnsfer pump house ) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
134 | Monorail beam with electrical hoist 1 Ton including cable trolley (Chemical dosing shed ) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
135 | Monorail beam with electrical hoist 1 Ton including cable trolley (SWRO/Back wash pump house) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
136 | Monorail beam with electrical hoist 3 Ton, including cable trolley ( Reject Outfall pump house) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
137 | Monorail beam with electrical hoist 2 Ton including cable trolley ( Final product pump house) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
138 | Monorail beam with electrical hoist 1Tonincluding cable trolley (Remin system feed pumphouse) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
139 | Monorail beam with Manual chain pully block (3 Ton) Filter Backwash Pump house including cable trolley, | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
140 | Monorail beam with electrical hoist 2 Ton including cable trolley(Lime Handling silo) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
141 | EOT Crane 10 Ton (Single Girder Crane for SWRO shed) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
142 | EOT Crane 10 Ton (Single Girder Crane for BWRO shed) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
143 | Monorail beam with electrical hoist 2 Ton including cable trolley (PSF& DMF Air blower room) | Nos | 1 | 140000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
T20 | STRUCTURE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | Fabrication and installation of Ladders Platforms, Pipe Rack, Pipe supports, Cable tray supports, Valve supports etc | Ton | 250 | 42000 | 10500000 | 25 | 35 | 60 | 1050000 | 1470000 | 2520000
145 | Installation of Prefabricated Ladders Platforms, Handrail, Pipe supports, Cable tray supports, Valve supports, GRP pipe shaddle support with gasket & hardware, flange support (Site welding all be considered to weld on insert plate or base plate of supports),Grating ,FRP Sheets | Ton | 130 | 22000 | 2860000 | 36 | 40 | 76 | 792000 | 880000 | 1672000
146 | intermediate -1 coat and finish paint- 2 coat | Ton | 325 | 24000 | 7800000 | 14.76 | 25 | 39.76 | 354240 | 600000 | 954240
U21 | Unloading and storage of material | Ton | 5000 | 790.07 | 3950350 | 0 | 0 | 0 | 0 | 0 | 0
147 | Expansion Bellow | Nos | 10 | 2200 | 22000 | 0 | 0 | 0 | 0 | 0 | 0
148 | Civil Tank Wall Mounted Gate |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | Sluice Gate-Clear water storage tank | Nos | 2 | 38400 | 76800 | 0 | 0 | 0 | 0 | 0 | 0
150 | Sluice Gate-Clear water storage tank Launder | Nos | 2 | 28000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0
151 | Sluice Gate-SWRO productwater tank Launder | Nos | 2 | 28000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0
152 | Sluice Gate-SWRO productwater tank | Nos | 2 | 28000 | 56000 | 1.5 | 0 | 1.5 | 42000 | 0 | 42000
153 | Sluice Gate-Final product water tank | Nos | 2 | 28000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0
154 | Pipe Tray for CPVC pipe |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 50 Wide Ladder Type Cable Tray. | Mtr | 1000 | 200 | 200000 | 0 | 0 | 0 | 0 | 0 | 0
156 | 150 Wide Ladder Type Cable Tray. | Mtr | 1500 | 250 | 375000 | 0 | 0 | 0 | 0 | 0 | 0
157 | 300 Wide Ladder Type Cable Tray. | Mtr | 1500 | 400 | 600000 | 0 | 0 | 0 | 0 | 0 | 0
158 | 600 Wide Ladder Type Cable Tray. | Mtr | 1500 | 450 | 675000 | 0 | 0 | 0 | 0 | 0 | 0
159 | Earthing GI Flat-75x10mm,50x6mm | Mtr | 2000 | 250 | 500000 | 1424 | 0 | 1424 | 356000 | 0 | 356000
160 | Provide the precommissioning & Commissioning support for 120 working days as per Annex#1 | Days | 120 | 19350 | 2322000 | 0 | 0 | 0 | 0 | 0 | 0
161 | Provide below manpower for material control & Help Store function @ 180 days |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | Helper @Rs 1100 per day | Nos | 2 | 1050 | 378000 | 0 | 0 | 0 | 0 | 0 | 0
163 | Rigger @Rs 1200 per day | Nos | 1 | 1150 | 207000 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  |  |  | 105000000 |  |  |  | 35922257.2 | 5988092.8 | 41918600

## PAINTING
MEASURMENT SHEET FOR PAINTING
S.NO | DRW NO | WEIGHT (KG) | REMARKS
1 | E-10055-DW-MD-004K12P (RACK 2) | 3296
2 | E-10055-DW-MD-004K12P(RACK 15) | 1463
3 | E-10055-DW-MD-004K2-P | 5991.84
4 | E-10055-DW-MD-004K1-P | 0.234
5 | E-10055-DW-MD-004K5-P | 1840
6 | ECR-2 SUPPORTS | 1485
14076.074

## MANPOWER
MEASURMENT SHEET FOR MANPOWER SUPPLY
S.NO | DESCRIPTION | DATE | FITTER | WELDER | RIGGER | HELPER
1 | RAIL FIXING FOR CLIENT |  | 1 | 1 | 1 | 2
2 | RAIL FIXING FOR CLIENT |  | 1 | 1 | 1 | 2
3 | RAIL FIXING FOR CLIENT |  | 1 | 1 | 1 | 2
4 | WELDING OF RAIL |  | 0 | 1 | 0 | 1
5 | WELDING OF RAIL |  | 0 | 1 | 0 | 1
6 | WELDING OF RAIL |  | 0 | 1 | 0 | 1
7 | RAIL FIXING FOR CLIENT |  | 1 | 1 | 1 | 2
8 | INSTALLATION OF CURVE ANGLE INSIDE ECR ROOM 1 |  | 1 | 1 | 1 | 2
9 | INSTALLATION OF CURVE ANGLE INSIDE ECR ROOM 1 |  | 1 | 1 | 1 | 2
|  |  | 6 | 9 | 6 | 15
QTY NOT MENTIONED IN THE ABSTRACT ONCE SRINIVASA RAO SIR APPROVED WE WILL CLAIMED IT.

## PRE-FABRICATED STRUCTURE
MESURMENT SHEET FOR INSTALATION OF PRE-FABRICTED LADDER PLATFORM ND RO SKID
S.NO | DRW NO | DESCRIPTION | WEIGHT (KG) | REMARKS
1 | E-10055-DW-MD-105K51 | TOP LADDER AND PLATFORM FOR DAUL MEDIA FILTER | 14314.5 | 16 TON CLAIMED IN RA04 & BALANCE QTY PENDING DUE TO PROTOCOL SIGN NOT DONE
2 | E-10055-DW-MD-104K51 | TOP LADDER AND PLATFORM FOR PRESSURE SAND FILTER | 14314.5
3 | E-10055-DW-MD-110K51 | LADDER AND PLATFORM FOR LIME STONE MEDIA | 12800
4 | E-10055-DW-MD-419K1-P | SWRO SKID-D | 7709.3
5 | E-10055-DW-MD-419K1-P | SWRO SKID-E | 7709.3
6 | E-10055-DW-MD-419K1-P | SWRO SKID-A | 7709.3
7 | E-10055-DW-MD-419K1-P | SWRO SKID-B | 7709.3
8 |  | CATRIDGE FILTER LADDER PLATFROM | 10000
82266.2
|  | QTY CLAIMED IN RA04 | 16000
|  | QTY CLAIMED IN RA05 | 20000
|  | TOTAL QTY CLAIMED TILL NOW | 36000
|  | BALANCE QTY TO CLAIM | 46266.2

## structure fab & ere
MESURMENT SHEET FOR STRUCTURL STEEL FABRICTION AND ERECTION
SrNo | Drw No | Pipe Support/Rack No | Qty | Weight(KG) | Total Weight In Kg | Remark
1 | E-10055-DW-MD-004K2-P | PS-2123 A to F | 6 | 4.18 | 25.08
2 | E-10055-DW-MD-004K2-P | PS-2044 to 2062 | 18 | 10.03 | 180.54
3 | E-10055-DW-MD-004K2-P | PS-2064 to 2082 | 18 | 10.03 | 180.54
4 | E-10055-DW-MD-004K2-P | PS-2102 to 2120 | 18 | 10.03 | 180.54
5 | E-10055-DW-MD-004K2-P | PS-2083 to 2100 | 18 | 10.03 | 180.54
6 | E-10055-DW-MD-004K2-P | PS-2012 K to N, P to T | 18 | 26.68 | 480.24
7 | E-10055-DW-MD-004K2-P | PS-2012 A to H & J | 18 | 26.68 | 480.24
8 | E-10055-DW-MD-004K2-P | PS-2009 K to N,P to T | 18 | 20.81 | 374.58
9 | E-10055-DW-MD-004K2-P | PS-2009 A to H & J | 18 | 20.81 | 374.58
10 | E-10055-DW-MD-004K2-P | PS-2008 K to N,P to T | 18 | 9.15 | 164.7 |  | only fabrication done
11 | E-10055-DW-MD-004K2-P | PS-2008 A to H & J | 18 | 9.15 | 164.7 |  | erection & fab done
12 | E-10055-DW-MD-004K2-P | PS-2002 K to N,P to T | 18 | 11.7 | 210.6
13 | E-10055-DW-MD-004K2-P | PS-2002 A to H & J | 18 | 11.7 | 210.6
14 | E-10055-DW-MD-004K2-P | PS-2001 K to N,P to T | 18 | 32.75 | 589.5
15 | E-10055-DW-MD-004K2-P | PS-2001 A to H & J | 18 | 32.75 | 589.5
16 | E-10055-DW-MD-004K2-P | PS-2020 A to J | 9 | 19.63 | 176.67
17 | E-10055-DW-MD-004K2-P | PS-2004 A to H & J | 9 | 14.22 | 127.98
18 | E-10055-DW-MD-004K2-P | PS-2023 A to J | 18 | 21.64 | 389.52
19 | E-10055-DW-MD-004K2-P | PS-2003 A to H & J | 9 | 21.56 | 194.04 | DMF-2
20 | E-10055-DW-MD-004K2-P | PS-2003 K to N,P to T | 9 | 21.56 | 194.04 | PSF-2
21 | E-10055-DW-MD-004K2-P | PS-2005 A to H & J | 9 | 19.63 | 176.67 | DMF-2
22 | E-10055-DW-MD-004K2-P | PS-2005 K to N,P to T | 9 | 19.63 | 176.67 | PSF-2
23 | E-10055-DW-MD-004K2-P | PS-2006 A to H & J | 9 | 19.63 | 176.67 | DMF-2
24 | E-10055-DW-MD-004K2-P | PS-2006 K to N,P to T | 9 | 19.63 | 176.67 | PSF-2
25 | E-10055-DW-MD-004K2-P | PS-2007 A to H & J | 9 | 19.63 | 176.67 | DMF-2
26 | E-10055-DW-MD-004K2-P | PS-2007 K to N,P to T | 9 | 19.63 | 176.67 | PSF-2
27 | E-10055-DW-MD-004K2-P | PS-2022 A to J | 9 | 20.81 | 187.29
28 | E-10055-DW-MD-004K2-P | PS-2022 K to T | 9 | 20.81 | 187.29
29 | E-10055-DW-MD-004K5-P | PS-1587 A & B | 2 | 33.48 | 66.96
30 | E-10055-DW-MD-004K5-P | PS-1570 A & B | 2 | 33.48 | 66.96
31 | E-10055-DW-MD-004K5-P | PS-1567 | 1 | 26.38 | 26.38
32 | E-10055-DW-MD-004K5-P | PS-1599 A & B | 2 | 34.45 | 68.9
33 | E-10055-DW-MD-004K5-P | PS-1588 | 1 | 6.66 | 6.66
34 | E-10055-DW-MD-004K5-P | PS-1589 | 1 | 4.84 | 4.84
35 | E-10055-DW-MD-004K5-P | PS-1597 | 1 | 5.28 | 5.28
36 | E-10055-DW-MD-004K5-P | PS-1002 A,B,C,D,E | 5 | 175.12 | 875.6
37 | E-10055-DW-MD-004K5-P | PS-1003 A,B,C,D,E | 5 | 104.88 | 524.4
38 | E-10055-DW-MD-004K5-P | PS-1600 | 1 | 5.1 | 5.1
39 | E-10055-DW-MD-004K5-P | PS-1569 A & B | 2 | 18.41 | 36.82
40 | E-10055-DW-MD-004K5-P | PS-1571 | 1 | 6.71 | 6.71
41 | E-10055-DW-MD-004K5-P | PS-1576 | 1 | 4.82 | 4.82
42 | E-10055-DW-MD-004K5-P | PS-1566 | 1 | 4.9 | 4.9
43 | E-10055-DW-MD-004K5-P | PS-1586 A & B | 2 | 18.41 | 36.82
44 | E-10055-DW-MD-004K5-P | PS-1598 A & B | 2 | 19.36 | 38.72
45 | E-10055-DW-MD-004K5-P | PS-1572 | 1 | 4.94 | 4.94
46 | E-10055-DW-MD-004K5-P | PS-1577 A & B | 2 | 18.41 | 36.82
47 | E-10055-DW-MD-004K5-P | PS-1585 | 1 | 4.75 | 4.75
48 | E-10055-DW-MD-004K1-P | PS-1001 A,B,C,D,E | 5 | 37.83 | 189.15
49 | E-10055-DW-MD-004K1-P | PS-1004 | 1 | 29.42 | 29.42
50 | E-10055-DW-MD-004K1-P | PS-1005 | 1 | 13.71 | 13.71
51 | E-10055-DW-MD-004K12-P | Rack-12 | 1 | 3269.34 | 3269.34
52 | E-10055-DW-MD-004K13-P | Rack-16 | 1 | 11018.4 | 11018.4
53 | E-10055-DW-MD-004K12-P | Rack-15 | 1 | 1462.53 | 1462.53
54 | E-10055-DW-MD-004K12-P | Rack-17 | 1 | 4163.2 | 4163.2
55 | E-10055-DW-MD-004K11-P | Rack-01 | 1 | 12749 | 12749 | Actual weight
56 | E-10055-DW-MD-004K11-P | Rack-05 | 1 | 5037.83 | 5037.83
57 | E-10055-DW-MD-004K14-P | Rack-04 | 1 | 8815 | 8815
58 | ECR BUILDING -2 | PMCC Support | 1 | 1579 | 1579
| Total Weight in M.T |  |  |  | 57.0563
|  | Qty clamied in RA04 |  | 10000
|  | QTY clamied in RA05 |  | 15000

## G.I
S.NO | DRW NO | DESCRIPTION | SIZE(INCH) | LENGTH(M) | INCH/MTRS | REMARKS
1 | PA-200-CS-2402 | PLANT AIR LINE FOR DMF-1 | 8 | 82.55 | 660.4
2 | PA-200-CS-2402 | PLANT AIR LINE FOR DMF-2 | 8 | 82.55 | 660.4
1320.8

## Sheet1
|  | SKILLED | UNSKILLED
RO HOUSE | 17 | 7 | 10
G.I PIPING | 7 | 2 | 5
CER 2 | 8
36049.78*12
| 324448.02 | 200000 |  |  | 3
| 124448.02 |  |  | 555